|  |  |
| --- | --- |
| **Component 6.1: INCREASING RESILIENCE OF THE HEALTH SYSTEM** | |
| **Investment/ reform CID reference** | **Investment 1** |
| **Investment/ reform name** | **Creation of the Intensive Medicine Simulation Centre and optimisation of the education system** |
| **Type of change compared to CID** | [modified] |
| **Legal base of the change (select at least one)** | Article 14(2) – loan request  Article 18(2) – update of the maximum financial contribution  Article 21 – amendment due to objective circumstances  Article 21a – REPowerEU non-repayable financial support (ETS revenue)  Article 21b (2) – BAR transfers  ☐ None of the above, correction of clerical error |
| **Elements modified (only for modified measures)** | Component / Measure description  Milestones and targets  Estimated cost  Green and digital tagging (potentially relevant, because there is a substantive change to the underlying measure)  DNSH self-assessment |

|  |  |  |
| --- | --- | --- |
| **Investment 1: Creation of the Intensive Medicine Simulation Centre and optimisation of the edcuation systems – Milestone 233** | | |
| *Description and justification of the change* | | |
| **Modified elements** | **Current version** | **Amended version** |
| ***Component and / or measure description*** | *No change* | *No change* |
| ***Milestones and targets*** | *The Intensive Medicine Simulation Centre shall be constructed, fully equipped and put in operation. It shall be run by the Institute for Postgraduate Education in Healthcare. The capacity should be sufficient to ensure that at least 1 500 healthcare professionals shall be trained in the centre per year.* | *The Intensive Medicine Simulation Centre shall be constructed, fully equipped and put in operation. ~~It shall be run by the Institute for Postgraduate Education in Healthcare~~. The capacity should be sufficient to ensure that at least 1 500 healthcare professionals shall be trained in the centre per year* |
| ***Estimated cost*** | *No change* | *No change* |
| ***Green and digital tagging*** | *N/A* | *N/A* |
| ***DNSH self-assessment*** | *No change* | *No change* |

***Objective facts why the milestones and targets could not be met:***

*The modification requests a removal of the operator entity in the milestone/objective description.*

*The removal is requested due to the inability to achieve the previously anticipated operator. While the description of the milestone in terms of the operator cannot be met, the objective and substance of the milestone remain unchanged.*

*The investment (Intensive Care Simulation Centre) which is the subject of the support is currently being implemented by the Motol University Hospital. However, the description of the milestone states that the operator of this investment will be the Institute of Postgraduate Medical Education. On this basis, the designated operator should be removed from the milestone description. This fact is also mentioned in the verification mechanism, which would also have to be modified subsequently.*