|  |  |
| --- | --- |
| **Component 2.8: BROWNFIELDS REVITALISATION** | |
| **Investment/ reform CID reference** | **Investment 1** |
| **Investment/ reform name** | **Support for revitalisation of specific areas** |
| **Type of change compared to CID** | [modified] |
| **Legal base of the change (select at least one)** | Article 14(2) – loan request  Article 18(2) – update of the maximum financial contribution  Article 21 – amendment due to objective circumstances  Article 21a – REPowerEU non-repayable financial support (ETS revenue)  Article 21b (2) – BAR transfers  ☐ None of the above, correction of clerical error |
| **Elements modified (only for modified measures)** | Component / Measure description  Milestones and targets  Estimated cost  Green and digital tagging (potentially relevant, because there is a substantive change to the underlying measure)  DNSH self-assessment |

|  |  |  |
| --- | --- | --- |
| **Investment 1: Support for revitalisation of specific areas – Milestone 154** | | |
| *Description and justification of the change* | | |
| **Modified elements** | **Current version** | **Amended version** |
| ***Component and / or measure description*** | *The investment shall support brownfield regeneration projects aimed at preparing areas for further multifunctional use (including refurbishment and construction of infrastructure or demolition of buildings). Specific brownfield sites have been identified by the Ministry of Regional Development in cooperation with CzechInvest, the investment and business development agency of Czechia subordinate to the Ministry of Industry and Trade, based on the size of the site, the expected size of the investment and the alignment of the project with Europe’s green transition ambitions. The measure shall consist of the establishment of a subsidy programme which shall provide support for the preparation of land for future investments and for the investment projects themselves. The investment shall support 14 brownfield regeneration projects.* | *The investment shall support brownfield regeneration projects aimed at preparing areas for further multifunctional use (including refurbishment and construction of infrastructure or demolition of buildings). Specific brownfield sites have been identified by the Ministry of Regional Development in cooperation with CzechInvest, the investment and business development agency of Czechia subordinate to the Ministry of Industry and Trade, based on the size of the site, the expected size of the investment and the alignment of the project with Europe’s green transition ambitions. The measure shall consist of the establishment of a subsidy programme which shall provide support for the preparation of land for future investments and for the investment projects themselves. The investment shall support at least 10 brownfield regeneration projects.* |
| ***Milestones and targets*** | *Name:*  *Award of all public contracts for projects revitalising specific brownfields*  *Qualitative indicator:*  *Notification of the award of all public contracts for projects revitalising specific brownfields by the Ministry of Regional Development*  *Description:*  *Announcement of a subsidy program for specific brownfield site regeneration (project preparation, land preparation, investment projects) following the preparation of a subsidy program, which requires formal approval by the Ministry of Finance. The projects shall both be aimed at supporting demolition and energy-efficient construction as well as energy-efficient renovation. Concerning energy-efficient construction, the calls shall specify that the new buildings supported by the projects shall have a Primary Energy Demand (PED) that is at least 20 % lower than the NZEB requirement.*  *After evaluating the call, there shall be a list of recommended projects for support. Projects shall be pre-selected and recommended by regional permanent conferences. Every region shall recommend at least one project to be supported. At least one industrial site shall be supported in each region of Czechia, with the list of supported brownfields including the sites of Terezin and Josefov. Formal control of the projects shall be taken by the State Investment Fund.* | *Name:*  ***Signing of all subsidy contracts between the State Investment Fund and selected brownfield project holders.***  *Qualitative indicator:*  ***Signing of all subsidy contracts by the State Investment Fund.***  *Description:*  *Announcement of a subsidy program for specific brownfield site regeneration (project preparation, land preparation, investment projects) following the preparation of a subsidy program~~, which requires formal approval by the Ministry of Finance.~~ The subsidy programme shall both be aimed at supporting demolition and energy-efficient construction as well as energy-efficient renovation. Concerning energy-efficient construction, the calls shall specify that the new buildings supported by the projects shall have a Primary Energy Demand (PED) that is at least 20 % lower than the NZEB requirement.*  *~~After evaluating the call, there shall be a list of recommended projects for support. Projects shall be pre-selected and recommended by regional permanent conferences. Every region shall recommend at least one project to be supported. At least one industrial site shall be supported in each region of Czechia, with the list of supported brownfields including the sites of Terezin and Josefov. Formal control of the projects shall be taken by the State Investment Fund.~~*  *The management of the call, evaluation of project applications, selection and signing of a contract with project holders as well as payments during a project realization (construction) and final control shall be entrusted to the State Investment Fund.* |
| ***Estimated cost*** | *No change* | *No change* |
| ***Green and digital tagging*** | *No change* | *No change* |
| ***DNSH self-assessment*** | *No change* | *No change* |

The State Investment Fund is responsible for an implementation of the component. The Fund can sign a “subsidy contract”, as according to Czech legislation the award could be given to a project holder only by a Government body (for instance a Ministry or a State agency). For this reason, the milestone is in fact a number of signed contracts between the Fund and the project holders after the announcement and evaluation of the call.

The reduction of the number of projects is based on the yearly inflation (HICP) rate measured by EUROSTAT and its prospects up to 2024 (3.3 % in 2021, 14.8 % in 2022, 9.3% prediction for 2023 and 3.5 % prediction for 2024 with 2 % standard inflation measure reduction) combined with low absorption capacity as noticed during a year-long terrain survey among potential project holders started in March 2022. The rapid rise of the price of construction works and material supplies limits the overall number of projects available that can be financed under a constant budget and completed in 2025. A proportional reduction is applied to the minimum number of supported projects, which decreases from 14 to 10.

In addition, we cannot guarantee that each region will be able to supply at least one project in accordance with all the DNSH and CID rules, due to a complicated and thorough nature of BF projects. Half of the regions have so far none specific project, another 4 have only one project suitable for the program. So only 3 out of 14 regions would really pre-select anything. The other obstacle is a narrow definition of “industrial site” in CID description, which rules out any other railway, cultural, civic, military, etc. brownfields. The inclusion and explicit mention of Terezin and Josefov sites is contradictory to the “industrial site” definition, as these are rather unused military barrack brownfields. Thus, we suppose to omit these two sites from 2.8.1. Milestone description together with the pre-selection process of regional permanent conferences. The State Investment Fund role is described in more detail.

|  |  |
| --- | --- |
| **Component 2.8: BROWNFIELDS REVITALISATION** | |
| **Investment/ reform CID reference** | **Investment 1** |
| **Investment/ reform name** | **Support for revitalisation of specific areas** |
| **Type of change compared to CID** | [modified] |
| **Legal base of the change (select at least one)** | Article 14(2) – loan request  Article 18(2) – update of the maximum financial contribution  Article 21 – amendment due to objective circumstances  Article 21a – REPowerEU non-repayable financial support (ETS revenue)  Article 21b (2) – BAR transfers  ☐ None of the above, correction of clerical error |
| **Elements modified (only for modified measures)** | Component / Measure description  Milestones and targets  Estimated cost  Green and digital tagging (potentially relevant, because there is a substantive change to the underlying measure)  DNSH self-assessment |

|  |  |  |
| --- | --- | --- |
| **Investment 1: Support for revitalisation of specific areas – Target 155** | | |
| *Description and justification of the change* | | |
| **Modified elements** | **Current version** | **Amended version** |
| ***Component and / or measure description*** | *The investment shall support brownfield regeneration projects aimed at preparing areas for further multifunctional use (including refurbishment and construction of infrastructure or demolition of buildings). Specific brownfield sites have been identified by the Ministry of Regional Development in cooperation with CzechInvest, the investment and business development agency of Czechia subordinate to the Ministry of Industry and Trade, based on the size of the site, the expected size of the investment and the alignment of the project with Europe’s green transition ambitions. The measure shall consist of the establishment of a subsidy programme which shall provide support for the preparation of land for future investments and for the investment projects themselves. The investment shall support 14 brownfield regeneration projects.* | *The investment shall support brownfield regeneration projects aimed at preparing areas for further multifunctional use (including refurbishment and construction of infrastructure or demolition of buildings). Specific brownfield sites have been identified by the Ministry of Regional Development in cooperation with CzechInvest, the investment and business development agency of Czechia subordinate to the Ministry of Industry and Trade, based on the size of the site, the expected size of the investment and the alignment of the project with Europe’s green transition ambitions. The measure shall consist of the establishment of a subsidy programme which shall provide support for the preparation of land for future investments and for the investment projects themselves. The investment shall support at least 10 brownfield regeneration projects.* |
| ***Milestones and targets*** | *Quantitative indicator:*  *Number of projects: 14*  *Description:*  *30 % of the investment under this measure shall be aimed at supporting demolition and energy-efficient construction, and 70 % shall be aimed at supporting energy-efficient renovation of buildings on brownfield sites.*  *As to the funding of demolition and energy-efficient construction, it shall be ensured that the supported projects are such that (i) new buildings shall have a Primary Energy Demand (PED) that is at least 20 % lower than the NZEB requirement; (ii) deep renovation is not possible due to technical, health/safety or fit-for-purpose reasons; (iii) a maximum of 5 % new land shall be used at the place where the former building was located. This excludes the possibility of demolishing buildings in one place and constructing a building on another site instead.*  *Concerning the support of renovation activities, it shall be ensured that at least 90% of the costs shall support energy-efficiency renovations.*  *The total budget executed for this purpose over the duration of the measure shall amount to at least EUR 79 000 000.* | *Quantitative indicator:*  *Number of projects: 10*  *Description:*  *At least 60 % of the investment support provided under this measure shall be aimed at supporting energy-efficient renovation of buildings on brownfield sites.*  *As to the funding of demolition and energy-efficient construction, it shall be ensured that the supported projects are such that (i) new buildings shall have a Primary Energy Demand (PED) that is at least 20 % lower than the NZEB requirement; (ii) deep renovation is not possible due to technical, health/safety or fit-for-purpose reasons; (iii) the total built-up area of new buildings cannot exceed the total built-up area of all demolished former buildings of a brownfield site, with at least 80 % of the new buildings built-up area being placed directly on the built-up area of the former demolished buildings. The conversion of valuable green areas (of high biodiversity value) shall be excluded.*  *Concerning the support of renovation activities, it shall be ensured that at least 90% of the costs shall support energy-efficiency renovations.* |
| ***Estimated cost*** | *No change* | *No change* |
| ***Green and digital tagging*** | *No change* | *No change* |
| ***DNSH self-assessment*** | *No change* | *No change* |

|  |  |
| --- | --- |
| **Component 2.8: BROWNFIELDS REVITALISATION** | |
| **Investment/ reform CID reference** | **Investment 2** |
| **Investment/ reform name** | **Support for the revitalisation of areas in public ownership for non-business use** |
| **Type of change compared to CID** | [modified] |
| **Legal base of the change (select at least one)** | Article 14(2) – loan request  Article 18(2) – update of the maximum financial contribution  Article 21 – amendment due to objective circumstances  Article 21a – REPowerEU non-repayable financial support (ETS revenue)  Article 21b (2) – BAR transfers  ☐ None of the above, correction of clerical error |
| **Elements modified (only for modified measures)** | Component / Measure description  Milestones and targets  Estimated cost  Green and digital tagging (potentially relevant, because there is a substantive change to the underlying measure)  DNSH self-assessment |

|  |  |  |
| --- | --- | --- |
| **Investment 2: Support for the revitalisation of areas in public ownership for non-business use – Milestone 156** | | |
| *Description and justification of the change* | | |
| **Modified elements** | **Current version** | **Amended version** |
| ***Component and / or measure description*** | *The investment shall support the regeneration of brownfield sites owned by local and regional authorities that shall be turned into an amenity or a public institution, such as a school, a cultural centre, a sports ground, a municipal authority or a publicly accessible park. Support shall exclusively be given to projects that commit either to energy-efficient renovation or the creation of natural carbon sinks, including the creation of permanent grassland or the planting of trees. The investment shall support 45 non-business brownfield regeneration projects.* | *The investment shall support the regeneration of brownfield sites owned by local and regional authorities that shall be turned into an amenity or a public institution, such as a school, a cultural centre, a sports ground, a municipal authority or a publicly accessible park. Support shall exclusively be given to projects that commit either to energy-efficient renovation or the creation of natural carbon sinks, including the creation of permanent grassland or the planting of trees. The investment shall support at least 30 non-business brownfield regeneration projects.* |
| ***Milestones and targets*** | *Name:*  *Award of all public contracts for projects revitalising specific brownfields*  *Qualitative indicator:*  *Notification of the award of all public contracts for projects revitalising specific brownfields by the Ministry of Regional Development*  *Description:*  *Announcement of calls for regeneration of publicly owned brownfields following the preparation of a subsidy program, which requires formal approval by the Ministry of Finance. The projects shall both support energy-efficient renovation and measures aimed at turning industrial sites and contaminated land into a natural carbon sink.*  *Projects shall be contracted in two phases: first, by 31 December 2022, at least 35 projects shall be contracted. Second, by 31 December 2023, at least 10 additional projects shall be contracted.* | *Name:*  ***Signing of all contracts between the State Investment Fund and selected brownfield project holders.***  *Qualitative indicator:*  *Signing of all „subsidy contracts” by the State Investment Fund.*  *Description:*  *Announcement of calls for regeneration of publicly owned brownfields following the preparation of a subsidy program~~, which requires formal approval by the Ministry of Finance.~~ The ~~projects~~ subsidy programme shall both support energy-efficient renovation and measures aimed at turning ~~industrial~~* ***brownfields*** *sites ~~and contaminated land~~ into a natural carbon sink.*  *~~Projects shall be contracted in two phases: first, by 31 December 2022, at least 35 projects shall be contracted. Second, by 31 December 2023, at least 10 additional projects shall be contracted.~~*  *Overall, at least 30 projects shall be contracted.* |
| ***Estimated cost*** | *No change* | *No change* |
| ***Green and digital tagging*** | *No change* | *No change* |
| ***DNSH self-assessment*** | *No change* | *No change* |

***Objective facts why the milestones and targets could not be met***

The State Investment Fund is responsible for an implementation of the component. The Fund can sign a “support contract”, as according to Czech legislation the award may be given to a project holder only by a government body (for instance a Ministry or a State agency). For this reason, the milestone is in fact a number of signed contracts between the Fund and the project holders after the announcement and evaluation of the call.

The reduction of the number of projects is based on the yearly inflation (HICP) rate measured by EUROSTAT and its prospects up to 2024 (3.3 % in 2021, 14.8 % in 2022, 9.3% prediction for 2023 and 3.5 % prediction for 2024 with 2 % standard inflation measure reduction) combined with low absorption capacity as noticed during a year-long terrain survey among potential project holders started in March 2022. The rapid rise of the price of construction works and material supplies limits the overall number of projects available that can be financed under a constant budget and completed in 2025. A proportional reduction is applied to the minimum number of supported projects, which decreases from 45 to 30. In addition, the number of sqm of a build-up area is corrected to ensure consistency between the target’s description and its calculation (build-up area rather than brownfield size) and rely on the most up-to-date estimations. The target is consequently lowered from 94 000 sqm to 41 000 sqm.

Investment 2.8.1 is no longer totally achievable in its original format because unexpected technical difficulties have led to the need to modify certain aspects of the measure in order to implement more adequate and efficient solutions. As evidenced by the results of the first calls of projects launched in January 2023, the 5% conditional rule on build-up area included in the original CID proved extremely difficult to implement in practice and to adversely affect the roll-out of this investment measure as the selection body had to reject several applications despite the latter complying with the measure’s policy and environmental objectives. Out of the 10 applications received so far, only two have met the original rule as the technical feature of the rule in accordance with the definition provided in Czech Building Code has created unforeseen consequences. For these reasons, and in line with art.21 of the RRF Regulation, we propose to adjust this requirement to clarify its objectives and facilitate its implementation while preserving the measure’s environmental ambition. While providing more clarity, the new description of the conditionality is also stricter and explicitly states the obligation to save valuable biodiversity areas and not to convert them during the revitalization. Also the limit of original built-up area, which cannot be exceeded by new buildings built-up area is explictily spelled-out and stricter than the former conditionality. The change is clear and the rule now complies with the Czech building code, which makes the Call more transparent for applicants and the State Investment Fund may verify it without uncertainties.

|  |  |
| --- | --- |
| **Component 2.8: BROWNFIELDS REVITALISATION** | |
| **Investment/ reform CID reference** | **Investment 2** |
| **Investment/ reform name** | **Support for the revitalisation of areas in public ownership for non-business use** |
| **Type of change compared to CID** | [modified] |
| **Legal base of the change (select at least one)** | Article 14(2) – loan request  Article 18(2) – update of the maximum financial contribution  Article 21 – amendment due to objective circumstances  Article 21a – REPowerEU non-repayable financial support (ETS revenue)  Article 21b (2) – BAR transfers  ☐ None of the above, correction of clerical error |
| **Elements modified (only for modified measures)** | Component / Measure description  Milestones and targets  Estimated cost  Green and digital tagging (potentially relevant, because there is a substantive change to the underlying measure)  DNSH self-assessment |

|  |  |  |
| --- | --- | --- |
| **Investment 2: Support for the revitalisation of areas in public ownership for non-business use – Target 157** | | |
| *Description and justification of the change* | | |
| **Modified elements** | **Current version** | **Amended version** |
| ***Component and / or measure description*** | *The investment shall support the regeneration of brownfield sites owned by local and regional authorities that shall be turned into an amenity or a public institution, such as a school, a cultural centre, a sports ground, a municipal authority or a publicly accessible park. Support shall exclusively be given to projects that commit either to energy-efficient renovation or the creation of natural carbon sinks, including the creation of permanent grassland or the planting of trees. The investment shall support 45 non-business brownfield regeneration projects.* | *The investment shall support the regeneration of brownfield sites owned by local and regional authorities that shall be turned into an amenity or a public institution, such as a school, a cultural centre, a sports ground, a municipal authority or a publicly accessible park. Support shall exclusively be given to projects that commit either to energy-efficient renovation or the creation of natural carbon sinks, including the creation of permanent grassland or the planting of trees. The investment shall support at least 30 non-business brownfield regeneration projects.* |
| ***Milestones and targets*** | *Quantitative indicator:*  *Number of m2 of revitalised buildings footprint*  *Goal:*  *94 000 m2*  *Description:*  *80 % of the investment shall support energy-efficient renovation, and 20 % shall be aimed at measures aimed at turning industrial sites and contaminated land into a natural carbon sink. Overall, at least 45 projects shall be completed.*  *Concerning the support of renovation activities, it shall be ensured that at least 90 % of the costs shall support energy-efficiency renovations.* | *Quantitative indicator:*  *Number of m2 of revitalised build-up area*  *Goal:*  *41 000 m2*  *Description:*  *~~80 % of the investment shall support energy-efficient renovation, and~~ At least 20 % of the investment shall ~~be aimed at~~support measures aimed at turning ~~industrial~~ brownfields sites ~~and contaminated land~~ into ~~a~~ natural carbon sinks. Overall, at least ~~45~~ 30 projects shall be completed.*  *Concerning the support of renovation activities, it shall be ensured that at least 90 % of the costs shall support energy-efficiency renovations.* |
| ***Estimated cost*** | *No change* | *No change* |
| ***Green and digital tagging*** | *No change* | *No change* |
| ***DNSH self-assessment*** | *No change* | *No change* |

***Objective facts why the milestones and targets could not be met***

The State Investment Fund is responsible for an implementation of the component. The Fund can sign a “support contract”, as according to Czech legislation the award may be given to a project holder only by a government body (for instance a Ministry or a State agency). For this reason, the milestone is in fact a number of signed contracts between the Fund and the project holders after the announcement and evaluation of the call.

The reduction of the number of projects is based on the yearly inflation (HICP) rate measured by EUROSTAT and its prospects up to 2024 (3.3 % in 2021, 14.8 % in 2022, 9.3% prediction for 2023 and 3.5 % prediction for 2024 with 2 % standard inflation measure reduction) combined with low absorption capacity as noticed during a year-long terrain survey among potential project holders started in march 2022. The rapid rise of the price of construction works and material supplies limits the overall number of projects that can be financed under a constant budget and completed in 2025. A proportional reduction is applied to the minimum number of supported projects, which decreases from 45 to 30. In addition, the number of sqm of a build-up area is corrected to ensure consistency between the target’s description and its calculation (build-up area rather than brownfield size) and rely on the most up-to-date estimations. The target is consequently lowered from 94 000 sqm to 41 000 sqm

|  |  |
| --- | --- |
| **Component 2.8: BROWNFIELDS REVITALISATION** | |
| **Investment/ reform CID reference** | **Investment 3** |
| **Investment/ reform name** | **Support for the revitalisation of areas in public ownership for business use** |
| **Type of change compared to CID** | [modified] |
| **Legal base of the change (select at least one)** | Article 14(2) – loan request  Article 18(2) – update of the maximum financial contribution  Article 21 – amendment due to objective circumstances  Article 21a – REPowerEU non-repayable financial support (ETS revenue)  Article 21b (2) – BAR transfers  ☐ None of the above, correction of clerical error |
| **Elements modified (only for modified measures)** | Component / Measure description  Milestones and targets  Estimated cost  Green and digital tagging (potentially relevant, because there is a substantive change to the underlying measure)  DNSH self-assessment |

|  |  |  |
| --- | --- | --- |
| **Investment 3: Support for the revitalisation of areas in public ownership for business use – Target 158** | | |
| *Description and justification of the change* | | |
| **Modified elements** | **Current version** | **Amended version** |
| ***Component and / or measure description*** | *The investment shall help revitalise brownfield degraded sites, including the removal of small-scale obstacles on the surface, owned by municipalities in particular for business use and, to a limited extent, for non-business use. These obstacles refer to parts of constructions marked as hazardous waste, such as asbestos-containing materials, or small oil leaks. A particular emphasis shall be placed on strict adherence to the principles of blue-green infrastructure and energy efficiency, implying that preference shall be given to projects implementing rainwater management pursuant to Act 254/2001 (“Water Act”) and, in case of new buildings, energy savings measures beyond the legislative requirements of Act 406/2000 (“Energy Management Act”). Regenerated sites shall be used prefereably by small- and medium sized enterprises and local firms. The investment shall support projects to revitalise brownfield sites for business use corresponding to the target of at least 76000 m3 of built-up space.*  *The investment shall be completed by 31 December 2025.* | *No change* |
| ***Milestones and targets*** | *Description:*  *Announcement of calls for regeneration of publicly owned brownfields following the preparation of a subsidy program. The projects shall both be aimed at supporting demolition and energy-efficient construction as well as energy-efficient renovation. Concerning energy-efficient construction, the calls shall specify that the supported projects are such that new buildings shall have a Primary Energy Demand (PED) that is at least 20 % lower than the NZEB requirement.*  *Projects shall be contracted in two phases: first, by 31 December 2022, at least 15 projects shall be contracted. Second, by 31 December 2023, at least 5 additional projects shall be contracted.* | *Description:*  *Announcement of calls for regeneration of publicly owned brownfields following the preparation of a subsidy program. The ~~projects~~ subsidy programme shall both be aimed at supporting demolition and energy-efficient construction as well as energy-efficient renovation. Concerning energy-efficient construction, the calls shall specify that the supported projects are such that new buildings shall have a Primary Energy Demand (PED) that is at least 20 % lower than the NZEB requirement.*  *Projects shall be contracted ~~in two phases: first, by 31 December 2022, at least 15 projects shall be contracted. Second,~~ by 31 December 2023 at the latest. ~~least 5 additional projects shall be contracted.~~* |
| ***Estimated cost*** | *No change* | *No change* |
| ***Green and digital tagging*** | *No change* | *No change* |
| ***DNSH self-assessment*** | *No change* | *No change* |

|  |  |
| --- | --- |
| **Component 2.8: BROWNFIELDS REVITALISATION** | |
| **Investment/ reform CID reference** | **Investment 3** |
| **Investment/ reform name** | **Support for the revitalisation of areas in public ownership for business use** |
| **Type of change compared to CID** | [modified] |
| **Legal base of the change (select at least one)** | Article 14(2) – loan request  Article 18(2) – update of the maximum financial contribution  Article 21 – amendment due to objective circumstances  Article 21a – REPowerEU non-repayable financial support (ETS revenue)  Article 21b (2) – BAR transfers  ☐ None of the above, correction of clerical error |
| **Elements modified (only for modified measures)** | Component / Measure description  Milestones and targets  Estimated cost  Green and digital tagging (potentially relevant, because there is a substantive change to the underlying measure)  DNSH self-assessment |

|  |  |  |
| --- | --- | --- |
| **Investment 3: Support for the revitalisation of areas in public ownership for business use – Target 159** | | |
| *Description and justification of the change* | | |
| **Modified elements** | **Current version** | **Amended version** |
| ***Component and / or measure description*** | *The investment shall help revitalise brownfield degraded sites, including the removal of small-scale obstacles on the surface, owned by municipalities in particular for business use and, to a limited extent, for non-business use. These obstacles refer to parts of constructions marked as hazardous waste, such as asbestos-containing materials, or small oil leaks. A particular emphasis shall be placed on strict adherence to the principles of blue-green infrastructure and energy efficiency, implying that preference shall be given to projects implementing rainwater management pursuant to Act 254/2001 (“Water Act”) and, in case of new buildings, energy savings measures beyond the legislative requirements of Act 406/2000 (“Energy Management Act”). Regenerated sites shall be used prefereably by small- and medium sized enterprises and local firms. The investment shall support projects to revitalise brownfield sites for business use corresponding to the target of at least 76000 m3 of built-up space.*  *The investment shall be completed by 31 December 2025.* | *No change* |
| ***Milestones and targets*** | *Description:*  *30 % of the investment under this measure shall be aimed at supporting demolition and energy-efficient construction, and 70 % shall be aimed at supporting energy-efficient renovation of buildings on brownfield sites. Overall, at least 20 projects shall be completed.*  *As to the funding of demolition and energy-efficient construction, it shall be ensured that the supported projects are such that (i) new buildings shall have a Primary Energy Demand (PED) that is at least 20 % lower than the NZEB requirement; (ii) deep renovation is not possible due to technical, health/safety or fit-for-purpose reasons; (iii) a maximum of 5 % new land shall be used at the place where the former building was located. This excludes the possibility of demolishing buildings in one place and constructing another building on another site instead.*  *Concerning the support of renovation activities, it shall be ensured that at least 90 % of the costs shall support energy-efficiency renovations.*  *The supervisory company of the grant provider (Ministry of Industry and Trade) shall carry out an on-site inspection of the work performed and compliance with project documentation and the calls for tender.* | *Description:*  *~~30 % of the investment under this measure shall be aimed at supporting demolition and energy-efficient construction, and 70~~ At least 60 % of the investment support provided under this measure shall be aimed at supporting energy-efficient renovation of buildings on brownfield sites. Overall, at least 20 projects shall be completed.*  *As to the funding of demolition and energy-efficient construction, it shall be ensured that the supported projects are such that (i) new buildings shall have a Primary Energy Demand (PED) that is at least 20 % lower than the NZEB requirement; (ii) deep renovation is not possible due to technical, health/safety or fit-for-purpose reasons; (iii) a maximum of 5 % new land shall be used at the place where the former building was located. This excludes the possibility of demolishing buildings in one place and constructing another building on another site instead.*  *Concerning the support of renovation activities, it shall be ensured that at least 90 % of the costs shall support energy-efficiency renovations.*  *~~The supervisory company of the grant provider (Ministry of Industry and Trade) shall carry out an on-site inspection of the work performed and compliance with project documentation and the calls for tender.~~* |
| ***Estimated cost*** | *No change* | *No change* |
| ***Green and digital tagging*** | *No change* | *No change* |
| ***DNSH self-assessment*** | *No change* | *No change* |